## Project Overview
APPLICATION PORTFOLIO RATIONALIZATION
PROJECT PLAN
Project Information
Project Name: | [Client Name] APR Engagement
Project Manager: | [PM Name]
Start Date: | 2025-11-22
End Date: | 2026-01-31
Duration: | 10 weeks
Phase Summary | Start | End | Duration
Phase 1: Initiation | Week 1 | Week 1 | 1 week
Phase 2: Discovery | Week 2 | Week 3 | 2 weeks
Phase 3: Assessment | Week 3 | Week 5 | 3 weeks
Phase 4: Analysis | Week 5 | Week 6 | 2 weeks
Phase 5: Recommendations | Week 6 | Week 8 | 3 weeks
Phase 6: Validation | Week 8 | Week 9 | 2 weeks
Phase 7: Delivery | Week 9 | Week 10 | 2 weeks

## Detailed Tasks
Task ID | Phase | Task Name | Description | Owner | Start Date | End Date | Duration (days) | Dependencies | Status | % Complete | Notes
1.1 | Initiation | Conduct kickoff meeting | Present project plan and objectives | PM |  |  | 1 |  | Not Started | 0%
1.2 | Initiation | Identify stakeholders | Create stakeholder registry | BA |  |  | 2 | 1.1 | Not Started | 0%
1.3 | Initiation | Inventory data sources | Document all available data sources | BA |  |  | 3 | 1.1 | Not Started | 0%
1.4 | Initiation | Setup project tools | Configure assessment tool access | PM |  |  | 3 | 1.1 | Not Started | 0%
1.5 | Initiation | Create communication plan | Define status reporting cadence | PM |  |  | 1 | 1.1 | Not Started | 0%
2.1 | Discovery | Extract CMDB data | Pull application inventory from CMDB | IT Ops |  |  | 3 | 1.3 | Not Started | 0%
2.2 | Discovery | Collect financial data | Gather cost data by application | Finance |  |  | 5 | 1.3 | Not Started | 0%
2.3 | Discovery | Gather usage metrics | Extract APM and usage data | Architect |  |  | 3 | 2.1 | Not Started | 0%
2.4 | Discovery | Map integrations | Document application dependencies | Architect |  |  | 3 | 2.1 | Not Started | 0%
2.5 | Discovery | Validate data quality | Assess completeness and accuracy | BA |  |  | 3 | 2.2,2.3 | Not Started | 0%
2.6 | Discovery | Document data gaps | Identify missing information | BA |  |  | 1 | 2.5 | Not Started | 0%
3.1 | Assessment | Customize questionnaire | Adapt questions for client context | BA |  |  | 1 | 2.5 | Not Started | 0%
3.2 | Assessment | Schedule interviews | Coordinate with stakeholders | PM |  |  | 2 | 1.2 | Not Started | 0%
3.3 | Assessment | Conduct interviews - Week 1 | Complete first batch of interviews | BA |  |  | 5 | 3.1,3.2 | Not Started | 0%
3.4 | Assessment | Conduct interviews - Week 2 | Complete second batch of interviews | BA |  |  | 5 | 3.3 | Not Started | 0%
3.5 | Assessment | Compile responses | Enter all responses into tool | BA |  |  | 2 | 3.4 | Not Started | 0%
3.6 | Assessment | Calculate assessment scores | Generate scores by category | BA |  |  | 1 | 3.5 | Not Started | 0%
3.7 | Assessment | Identify gaps | Note applications without assessment | BA |  |  | 1 | 3.6 | Not Started | 0%
4.1 | Analysis | Apply quantitative scoring | Score technical and cost metrics | Architect |  |  | 3 | 2.5 | Not Started | 0%
4.2 | Analysis | Integrate qualitative data | Combine with assessment scores | BA |  |  | 2 | 3.6,4.1 | Not Started | 0%
4.3 | Analysis | Apply TIME framework | Assign disposition to each app | Lead |  |  | 2 | 4.2 | Not Started | 0%
4.4 | Analysis | Perform cluster analysis | Group similar applications | Architect |  |  | 2 | 4.3 | Not Started | 0%
4.5 | Analysis | Identify opportunities | List potential savings/improvements | Lead |  |  | 2 | 4.4 | Not Started | 0%
5.1 | Recommendations | Develop retire recommendations | Detail decommission approach | Lead |  |  | 2 | 4.5 | Not Started | 0%
5.2 | Recommendations | Develop consolidate recommendations | Identify merge opportunities | Architect |  |  | 2 | 4.5 | Not Started | 0%
5.3 | Recommendations | Develop modernize recommendations | Plan enhancement initiatives | Architect |  |  | 2 | 4.5 | Not Started | 0%
5.4 | Recommendations | Develop replace recommendations | Identify SaaS alternatives | BA |  |  | 2 | 4.5 | Not Started | 0%
5.5 | Recommendations | Create implementation roadmap | Sequence all initiatives | Lead |  |  | 3 | 5.1-5.4 | Not Started | 0%
5.6 | Recommendations | Develop business case | Calculate ROI and payback | BA |  |  | 3 | 5.5 | Not Started | 0%
5.7 | Recommendations | Assess risks | Document risks and mitigations | Architect |  |  | 2 | 5.5 | Not Started | 0%
5.8 | Recommendations | Identify quick wins | List immediate opportunities | Lead |  |  | 1 | 5.5 | Not Started | 0%
6.1 | Validation | Conduct IT validation session | Review with technical team | Lead |  |  | 1 | 5.6 | Not Started | 0%
6.2 | Validation | Conduct business validation | Review with business owners | Lead |  |  | 1 | 6.1 | Not Started | 0%
6.3 | Validation | Incorporate feedback | Refine recommendations | Team |  |  | 3 | 6.2 | Not Started | 0%
6.4 | Validation | Prepare executive materials | Create presentation deck | Lead |  |  | 2 | 6.3 | Not Started | 0%
6.5 | Validation | Compile final report | Assemble all deliverables | BA |  |  | 2 | 6.3 | Not Started | 0%
7.1 | Delivery | Deliver executive presentation | Present to leadership | Lead |  |  | 1 | 6.4 | Not Started | 0%
7.2 | Delivery | Conduct tool training | Train client team on tool | Architect |  |  | 1 | 6.5 | Not Started | 0%
7.3 | Delivery | Document processes | Create process guides | BA |  |  | 2 | 7.1 | Not Started | 0%
7.4 | Delivery | Hand off data | Transfer all project data | PM |  |  | 1 | 7.2 | Not Started | 0%
7.5 | Delivery | Conduct closeout meeting | Formal project closure | Lead |  |  | 1 | 7.4 | Not Started | 0%
7.6 | Delivery | Collect feedback | Client satisfaction survey | PM |  |  | 1 | 7.5 | Not Started | 0%

## Stakeholder Registry
ID | Name | Title | Department | Email | Phone | Stakeholder Type | Applications | Influence | Interest | Communication Preference | Notes
S001 | John Smith | VP Operations | Operations | john.smith@client.com | 555-0101 | Executive | ERP, CRM | High | High | Email | Executive sponsor
S002 | Sarah Johnson | IT Director | IT | sarah.johnson@client.com | 555-0102 | Technical Lead | All | High | High | Teams | Key technical contact
S003 | Mike Chen | Finance Manager | Finance | mike.chen@client.com | 555-0103 | Business Owner | Finance Apps | Medium | High | Email | Cost data owner

## Deliverables Tracker
ID | Deliverable Name | Phase | Due Date | Owner | Reviewers | Status | Completion Date | Location | Notes
D001 | Project Charter | 1 |  | PM | Sponsor | Not Started
D002 | Stakeholder Registry | 1 |  | PM | Lead | Not Started
D003 | Application Inventory | 2 |  | BA | Architect | Not Started
D004 | Data Quality Report | 2 |  | BA | Lead | Not Started
D005 | Assessment Scores | 3 |  | BA | Lead | Not Started
D006 | TIME Disposition Matrix | 4 |  | Lead | Team | Not Started
D007 | Recommendation Report | 5 |  | Lead | Architect | Not Started
D008 | Implementation Roadmap | 5 |  | Architect | Lead | Not Started
D009 | Business Case | 5 |  | BA | Finance | Not Started
D010 | Executive Presentation | 6 |  | Lead | Sponsor | Not Started
D011 | Final Report | 6 |  | BA | Lead | Not Started
D012 | Training Materials | 7 |  | Architect | PM | Not Started

## Risk Register
ID | Risk Description | Category | Impact | Likelihood | Risk Score | Mitigation Strategy | Owner | Status | Notes
R001 | Incomplete or inaccurate data from source systems | Data | High | Medium | 6 | Early gap identification, multiple source triangulation | BA | Open
R002 | Key stakeholders unavailable for interviews | Resource | Medium | High | 6 | Flexible scheduling, backup interviewees, async options | PM | Open
R003 | Scope creep from additional application discovery | Scope | High | Medium | 6 | Clear scope definition, change control process | Lead | Open
R004 | Executive engagement and decision delays | Governance | High | Low | 3 | Regular updates, early preview, decision escalation | Lead | Open
R005 | Tool access or technical issues | Technical | Medium | Low | 2 | Early setup, backup procedures, IT support | PM | Open
R006 | Resistance to recommendations | Change | High | Medium | 6 | Early stakeholder involvement, validation sessions | Lead | Open