# Application Portfolio Rationalization

# Project Plan Template

Version: 1.0

Document Status: Template

Last Updated: November 2024

__________________________________________________

# Executive Summary

This project plan outlines the methodology and timeline for conducting an Application Portfolio Rationalization engagement. The engagement follows a structured 7-phase approach over 8-12 weeks to assess, analyze, and develop recommendations for the client's application portfolio.

__________________________________________________

# Project Overview

## Engagement Objectives

**Discover**: Establish complete inventory of all applications in scope

**Assess**: Evaluate each application across business, technical, and cost dimensions

**Analyze**: Apply rationalization framework to determine disposition recommendations

**Recommend**: Develop actionable roadmap with prioritized initiatives

**Enable**: Provide tools and processes for ongoing portfolio management

## Success Criteria

Complete application inventory with >95% coverage

Stakeholder interviews conducted for 80%+ of critical applications

Clear disposition recommendation for each application

Estimated cost savings identified and validated

Executive-ready deliverables and presentations

__________________________________________________

# Project Team

## Client Team

Role  |  Responsibility  |  Time Commitment

|------|----------------|-----------------|

Executive Sponsor  |  Decision authority, remove blockers  |  2-3 hrs/week

Project Lead  |  Day-to-day coordination, access facilitation  |  15-20 hrs/week

IT Architect  |  Technical assessment validation  |  10 hrs/week

Business Analyst  |  Business value validation  |  10 hrs/week

Data Provider(s)  |  CMDB, financial, usage data extraction  |  As needed

## Consulting Team

Role  |  Responsibility

|------|----------------|

Engagement Lead  |  Overall delivery, client relationship

Solution Architect  |  Technical assessment, recommendations

Business Analyst  |  Data collection, analysis, stakeholder interviews

Project Manager  |  Timeline, deliverables, status reporting

__________________________________________________

# Phase 1: Project Initiation (Week 1)

## Objectives

Establish project governance and communication

Confirm scope and success criteria

Set up project infrastructure

## Activities

Activity  |  Owner  |  Duration  |  Deliverable

|----------|-------|----------|-------------|

Kickoff meeting  |  Engagement Lead  |  2 hours  |  Kickoff deck, meeting notes

Stakeholder identification  |  Project Lead  |  2 days  |  Stakeholder registry

Data source inventory  |  Business Analyst  |  3 days  |  Data source catalog

Tool setup and access  |  Project Manager  |  3 days  |  Access confirmed

Communication plan  |  Project Manager  |  1 day  |  Communication matrix

## Key Milestones

[ ] Kickoff meeting completed

[ ] Project charter signed

[ ] All team members have required access

[ ] Weekly status meeting scheduled

## Deliverables

Project Charter

Stakeholder Registry

Communication Plan

Data Collection Plan

__________________________________________________

# Phase 2: Discovery & Data Collection (Weeks 2-3)

## Objectives

Gather comprehensive application inventory

Collect quantitative data from all sources

Identify data gaps and remediation approach

## Activities

Activity  |  Owner  |  Duration  |  Deliverable

|----------|-------|----------|-------------|

CMDB data extraction  |  Data Provider  |  3 days  |  Raw application list

Financial data collection  |  Business Analyst  |  5 days  |  Cost data by application

Usage/traffic data collection  |  Solution Architect  |  3 days  |  Usage metrics

Integration mapping  |  Solution Architect  |  3 days  |  Integration matrix

Data validation  |  Business Analyst  |  3 days  |  Validated dataset

## Data Sources

Source  |  Data Elements  |  Owner

|--------|---------------|-------|

CMDB/Asset Management  |  App name, owner, technology stack  |  IT Operations

Financial Systems  |  Licensing, infrastructure, support costs  |  Finance/IT Finance

APM/Monitoring  |  Usage patterns, performance metrics  |  IT Operations

HR Systems  |  FTE allocation, support resources  |  HR/PMO

Service Desk  |  Incident volume, support tickets  |  Service Desk

## Key Milestones

[ ] All data sources identified and access granted

[ ] Raw data extracted from all sources

[ ] Data quality issues documented

[ ] Preliminary application count established

## Deliverables

Application Inventory (Raw)

Data Quality Assessment

Gap Analysis Report

__________________________________________________

# Phase 3: Stakeholder Assessment (Weeks 3-5)

## Objectives

Conduct structured interviews with key stakeholders

Gather qualitative insights on business value and health

Validate and enrich quantitative data

## Activities

Activity  |  Owner  |  Duration  |  Deliverable

|----------|-------|----------|-------------|

Interview scheduling  |  Project Manager  |  2 days  |  Interview calendar

Questionnaire customization  |  Business Analyst  |  1 day  |  Customized questionnaire

Stakeholder interviews (30-40)  |  Business Analyst  |  10 days  |  Interview responses

Response compilation  |  Business Analyst  |  2 days  |  Assessment scores

Gap identification  |  Business Analyst  |  1 day  |  Missing assessment list

## Interview Structure

Each 45-60 minute interview covers:

**Business Value & Criticality** (10 min)

Revenue impact

Process dependency

Competitive advantage

**User Satisfaction** (8 min)

End user feedback

Support responsiveness

Documentation quality

**Technical Health** (10 min)

Stability and performance

Technology currency

Security compliance

**Change Readiness** (8 min)

Migration complexity

User resistance

Executive sponsorship

**Dependencies & Integration** (7 min)

Upstream/downstream systems

Integration complexity

**Cost Awareness** (5 min)

TCO understanding

Cost trends

**Future Needs** (7 min)

Strategic alignment

Growth capacity

## Key Milestones

[ ] 100% of scheduled interviews completed

[ ] All responses entered into assessment tool

[ ] Assessment scores calculated

[ ] Initial findings documented

## Deliverables

Completed Interview Responses

Stakeholder Assessment Report

Preliminary Insights Summary

__________________________________________________

# Phase 4: Analysis & Scoring (Weeks 5-6)

## Objectives

Apply rationalization framework to all applications

Generate disposition recommendations

Identify quick wins and high-impact opportunities

## Activities

Activity  |  Owner  |  Duration  |  Deliverable

|----------|-------|----------|-------------|

Quantitative scoring  |  Solution Architect  |  3 days  |  Technical scores

Qualitative integration  |  Business Analyst  |  2 days  |  Combined scores

TIME framework application  |  Engagement Lead  |  2 days  |  Disposition matrix

Cluster analysis  |  Solution Architect  |  2 days  |  Application clusters

Opportunity identification  |  Engagement Lead  |  2 days  |  Opportunity catalog

## Rationalization Framework (TIME)

Disposition  |  Criteria  |  Typical Action

|-------------|----------|----------------|

**Tolerate**  |  High business value, fair technical health  |  Maintain with minimal investment

**Invest**  |  High value, strategic importance  |  Modernize, enhance, scale

**Migrate**  |  Moderate value, poor health  |  Re-platform or re-host

**Eliminate**  |  Low value, high cost/risk  |  Retire, consolidate, replace

## Scoring Model

Overall Score = Weighted Average of:

Business Value (25%)

Technical Health (20%)

Cost Efficiency (15%)

User Satisfaction (15%)

Strategic Alignment (15%)

Risk Profile (10%)

## Key Milestones

[ ] All applications scored

[ ] Disposition assigned to each application

[ ] Top 10 opportunities identified

[ ] Analysis validated with client leads

## Deliverables

Scored Application Portfolio

TIME Disposition Matrix

Opportunity Catalog

Preliminary Savings Estimate

__________________________________________________

# Phase 5: Recommendations Development (Weeks 6-8)

## Objectives

Develop detailed recommendations for each disposition category

Create implementation roadmap

Quantify business case and ROI

## Activities

Activity  |  Owner  |  Duration  |  Deliverable

|----------|-------|----------|-------------|

Recommendation development  |  Engagement Lead  |  5 days  |  Detailed recommendations

Roadmap creation  |  Solution Architect  |  3 days  |  Implementation roadmap

Business case development  |  Business Analyst  |  3 days  |  ROI analysis

Risk assessment  |  Solution Architect  |  2 days  |  Risk register

Quick win identification  |  Engagement Lead  |  1 day  |  Quick win list

## Recommendation Categories

**Retire** (Eliminate)

Applications to decommission

Data migration/archival needs

Timeline and dependencies

**Consolidate** (Eliminate/Migrate)

Redundant applications to merge

Target platform selection

Migration approach

**Modernize** (Invest)

Applications for enhancement

Technology upgrade paths

Investment requirements

**Maintain** (Tolerate)

Applications with minimal changes

Support optimization

Cost reduction tactics

**Replace** (Migrate)

Applications for SaaS/commercial replacement

Vendor evaluation criteria

Transition approach

## Key Milestones

[ ] Recommendations documented for all applications

[ ] Roadmap draft completed

[ ] Business case validated

[ ] Executive preview conducted

## Deliverables

Recommendation Report

Implementation Roadmap

Business Case / ROI Analysis

Risk Register

__________________________________________________

# Phase 6: Validation & Refinement (Week 8-9)

## Objectives

Validate findings with key stakeholders

Incorporate feedback and refine recommendations

Prepare executive-ready materials

## Activities

Activity  |  Owner  |  Duration  |  Deliverable

|----------|-------|----------|-------------|

Working session #1 (IT)  |  Engagement Lead  |  4 hours  |  IT feedback

Working session #2 (Business)  |  Engagement Lead  |  4 hours  |  Business feedback

Recommendations refinement  |  Team  |  3 days  |  Updated recommendations

Executive materials prep  |  Engagement Lead  |  2 days  |  Executive deck

Final report compilation  |  Business Analyst  |  2 days  |  Final report

## Validation Checkpoints

Session  |  Participants  |  Focus

|---------|--------------|-------|

Technical Review  |  IT Architects, Ops Leads  |  Technical feasibility, dependencies

Business Review  |  Business Owners, Product Leads  |  Business impact, priorities

Financial Review  |  IT Finance, PMO  |  Cost estimates, budget alignment

Executive Preview  |  CIO/CTO, Business Executives  |  Strategic alignment, approval

## Key Milestones

[ ] All validation sessions completed

[ ] Feedback incorporated

[ ] Executive materials finalized

[ ] Final report approved

## Deliverables

Validation Session Notes

Refined Recommendations

Executive Presentation

Final Report

__________________________________________________

# Phase 7: Delivery & Knowledge Transfer (Weeks 9-10)

## Objectives

Present final findings to executive stakeholders

Transfer knowledge and tools to client team

Establish foundation for ongoing management

## Activities

Activity  |  Owner  |  Duration  |  Deliverable

|----------|-------|----------|-------------|

Executive presentation  |  Engagement Lead  |  2 hours  |  Presented findings

Tool training  |  Solution Architect  |  4 hours  |  Trained users

Process documentation  |  Business Analyst  |  2 days  |  Process guides

Data handoff  |  Project Manager  |  1 day  |  Complete dataset

Closeout meeting  |  Engagement Lead  |  1 hour  |  Project closure

## Knowledge Transfer Components

**Rationalization Tool Training**

Data import/export

Scoring model configuration

Report generation

**Process Documentation**

Annual refresh process

New application intake

Disposition workflow

**Governance Framework**

Roles and responsibilities

Decision criteria

Escalation paths

## Key Milestones

[ ] Executive presentation delivered

[ ] All team members trained

[ ] Documentation complete

[ ] Project formally closed

## Deliverables

Executive Presentation (Delivered)

Training Materials

Process Documentation

Complete Data Package

Project Closeout Report

__________________________________________________

# Risk Management

## Key Risks

Risk  |  Impact  |  Likelihood  |  Mitigation

|------|--------|------------|------------|

Incomplete data  |  High  |  Medium  |  Early gap identification, multiple sources

Stakeholder availability  |  Medium  |  High  |  Flexible scheduling, backup interviewees

Scope creep  |  High  |  Medium  |  Clear scope definition, change control

Data quality issues  |  High  |  Medium  |  Validation checkpoints, triangulation

Executive engagement  |  High  |  Low  |  Regular updates, early preview

__________________________________________________

# Success Metrics

Metric  |  Target  |  Measurement

|--------|--------|-------------|

Application coverage  |  >95%  |  Apps assessed / Total apps

Stakeholder participation  |  >80%  |  Interviews completed / Scheduled

Recommendation acceptance  |  >90%  |  Approved / Total recommendations

Identified savings  |  >15%  |  Annual savings / Current spend

Client satisfaction  |  >4.5/5  |  Survey score

__________________________________________________

# Communication Plan

## Regular Communications

Communication  |  Audience  |  Frequency  |  Owner

|---------------|----------|-----------|-------|

Status report  |  Project team, sponsors  |  Weekly  |  Project Manager

Steering committee  |  Executives  |  Bi-weekly  |  Engagement Lead

Working sessions  |  SMEs  |  As needed  |  Business Analyst

Executive updates  |  CIO/CTO  |  Phase milestones  |  Engagement Lead

## Status Report Template

Executive Summary

Accomplishments (past week)

Planned Activities (next week)

Risks and Issues

Decisions Needed

Key Metrics

__________________________________________________

# Appendices

## Appendix A: RACI Matrix

Activity  |  Sponsor  |  Project Lead  |  BA  |  Architect  |  PM

|----------|---------|--------------|----|-----------|----|

Approve charter  |  A  |  R  |  C  |  C  |  I

Data collection  |  I  |  A  |  R  |  C  |  C

Interviews  |  I  |  C  |  R  |  C  |  I

Analysis  |  I  |  C  |  R  |  R  |  I

Recommendations  |  A  |  C  |  R  |  R  |  C

Presentation  |  A  |  C  |  C  |  C  |  R

R = Responsible, A = Accountable, C = Consulted, I = Informed

## Appendix B: Glossary

Term  |  Definition

|------|------------|

APM  |  Application Portfolio Management

CMDB  |  Configuration Management Database

TCO  |  Total Cost of Ownership

TIME  |  Tolerate, Invest, Migrate, Eliminate

FTE  |  Full-Time Equivalent

## Appendix C: Document Change History

Version  |  Date  |  Author  |  Changes

|---------|------|--------|---------|

1.0  |  Nov 2024  |  [Author]  |  Initial release

__________________________________________________

This template should be customized for each engagement based on client-specific scope, timeline, and requirements.